## Workschedule
Order | Area | Module | Title | Subtitle | Dev % complete | Status
1 | 1 Existing Module Changes
2 |  | 1.1 Appointment Manager
3 |  |  | 1.1.1 Interface |  | 100% | Libraries upgraded
4 |  |  | 1.1.2 Linking facility |  | 50% | Linking engine in place but needs expansion for more than just Form
5 |  |  | 1.1.3 Filtering |  | 0% | Based on API
6 |  |  | 1.1.4 Appointment API |  | 10%
7 |  |  | 1.1.5 Data listing method |  | 0%
8 |  |  | 1.1.6 “Drag to edit” facility |  | 0%
9 |  |  | 1.1.7 “Email on edit” facility |  | 0%
10 |  | 1.2 Communications Centre
11 |  |  | 1.2.1 Attachments |  | 0%
12 |  |  | 1.2.2 Communications Report enhancement |  | 0%
13 |  |  | 1.2.3 Mail Merge issues |  | 0%
14 |  | 1.3 eCourse
15 |  |  | 1.3.1 New Table of Contents layout options
16 |  |  |  | 1.3.1.1 TOC’less. | 0%
17 |  |  |  | 1.3.1.2 The Moodle’esqe view. | 0%
18 |  |  |  | 1.3.1.3 The styled table of contents. | 0%
19 |  | 1.4 Form Management
20 |  |  | 1.4.1 Campaign table changes |  | 100%
21 |  |  | 1.4.2 Project Header |  | 100%
22 |  |  | 1.4.3 Inbox - onArrival matching engine |  | 100%
23 |  |  | 1.4.4 Form Prebuilds
24 |  |  |  | 1.4.4.1 Prebuild – Inbox manager | 90%
25 |  |  |  | 1.4.4.2 Prebuild – Outlook contacts exports | 0%
26 |  |  |  | 1.4.4.3 Prebuild – Contacts from emails | 0%
27 |  |  |  | 1.4.4.4 Prebuild – SalesForce data | 0%
28 |  |  |  | 1.4.4.5 Prebuild – ISO27001 SOA | 0%
29 |  |  |  | 1.4.4.6 Prebuild – Excel no data | 0%
30 |  |  | 1.4.5 Complex – Email Block change |  | 100%
31 |  |  | 1.4.6 Cross Linked report repair |  | 0%
32 |  |  | 1.4.7 Outbound Data Drill down |  | 0%
33 |  |  | 1.4.8 Create template from form |  | 0%
34 |  |  | 1.4.9 Word to form fix |  | 0%
35 |  |  | 1.4.10 Access on Pass |  | 0%
36 |  |  | 1.4.11 Outcome Exception Cost |  | 0%
37 |  |  | 1.4.12 Data Import timer |  | 0%
38 |  |  | 1.4.13 Record deletion audit log fix |  | 50%
39 |  |  | 1.4.14 Data Profiling - Instant Data Analysis |  | 100%
40 |  | 1.5 Information Centre
41 |  |  | 1.5.1 Scrolling Information Centre |  | 0%
42 |  |  | 1.5.2 Access by Security Groups |  | 0%
43 |  | 1.6 KeyStats
44 |  |  | 1.6.1 Console |  | 80%
45 |  |  | 1.6.2 Mass Edit Security |  | 20%
46 |  |  | 1.6.3 Hide Tabs |  | 50%
47 |  |  | 1.6.4 Syntax Highlighting |  | 100%
48 |  | 1.7 MetaData
49 |  |  | 1.7.1 Console |  | 80%
50 |  | 1.8 Project Manager
51 |  |  | 1.8.1 Gantt Chart interface |  | 0%
52 |  |  | 1.8.2 Project API |  | 0%
53 |  |  | 1.8.3 Costing |  | 80%
54 |  |  | 1.8.4 Scheduling |  | 0%
55 |  |  | 1.8.5 Exception Costs and API |  | 0%
56 |  |  | 1.8.6 Project Costs report |  | 0%
57 |  |  | 1.8.7 Project profile |  | 0%
58 |  |  | 1.8.8 Project Management console |  | 0%
59 |  |  | 1.8.9 User by project profile |  | 0%
60 |  | 1.9 System Access Management
61 |  |  | 1.9.1 User tabs |  | 100%
62 |  |  | 1.9.2 UAM “function” support engine |  | 50%
63 |  |  | 1.9.3 UAM and SAM wixis |  | 50%
64 |  |  | 1.9.4 Password blacklist engine |  | 0%
65 |  |  | 1.9.5 Client table alterations |  | 50%
66 |  |  | 1.9.6 Security - Retired date time |  | 0%
67 |  |  | 1.9.7 System Settings - Tabbed view |  | 100%
68 |  |  | 1.9.8 System Keywords - Tabbed view |  | 100%
69 |  | 1.10 Time Tracker
70 |  |  | 1.10.1 Confirmation Engine |  | 0%
71 |  |  | 1.10.2 Limit project and work type by Costing |  | 0%
72 | 2 New Modules
73 |  | 2.1 Dashboards |  |  | 70%
74 |  | 2.2 Expenses Management |  |  | 0%
75 |  | 2.3 PO Module |  |  | 0%
76 |  | 2.4 Scheduler |  |  | 0%
77 | 3 Engine
78 |  | 3.1 KeyStats plan |  |  | 100%
79 |  | 3.2 Scheduled reports plan |  |  | 0%
80 |  | 3.3 Big reports plan |  |  | 0%
81 |  | 3.4 Analytics |  |  | 0%
82 |  | 3.5 Custom folder via sftp |  |  | 100%
83 |  | 3.6 API Tester Engine |  |  | 50%
84 |  | 3.7 API Hamster Report (Moss and others) |  |  | 50%
85 |  | 3.8 Table styling |  |  | 80%
86 |  | 3.9 System Wipe function |  |  | 0%
87 |  | 3.10 System notification emails |  |  | 0%
88 |  | 3.11 Client daily picture engine |  |  | 100%
89 |  | 3.12 Login page - Username autocomplete |  |  | 100%
90 |  | 3.13 AJAX engine - Title when no records |  |  | 0%

## Workitems
1.6.1 Console | 1.6 KeyStats
1.7.1 Console | 1.7 MetaData
2.1 Dashboards | Outbound
2.1 Dashboards | Membership
2.1 Dashboards | Inbox management
1.4.4.1 Prebuild – Inbox manager
1.4.4.2 Prebuild – Outlook contacts exports
1.4.4.3 Prebuild – Contacts from emails
1.4.4.4 Prebuild – SalesForce data
1.4.4.5 Prebuild – ISO27001 SOA
1.4.4.6 Prebuild – Excel no data
1.4.8 Create template from form
1.4.9 Word to form fix
1.4.10 Access on Pass
1.4.12 Data Import timer
1.4.13 Record deletion audit log fix
1.5.1 Scrolling Information Centre
1.5.2 Access by Security Groups
1.3.1.1 TOC’less.
1.3.1.2 The Moodle’esqe view.
1.3.1.3 The styled table of contents.
1.9.2 UAM “function” support engine
1.9.4 Password blacklist engine
1.9.5 Client table alterations
1.9.7 System Settings - Tabbed view